HRMS Software

Project Plan & Roadmap

20-Day Sprint with Intern Team

Prepared by: Nidhish Zala

Duration: 20 Days  |  Team: Interns

# 1. Project Overview

This document outlines the full plan for building an HRMS (Human Resource Management System) in 20 days with an intern team. The first 2 days are dedicated to onboarding and setup. The remaining 18 days cover active development, testing, and deployment.

# 2. HRMS Features

## 2.1  Core / Basic Features

These are must-have features that must be completed within the 20-day timeline:

| Module | Features | Details |
| --- | --- | --- |
| Employee Management | Profile CRUD, Departments | Add/edit/view employees, set departments & designations, employee IDs |
| Attendance Tracking | Clock In/Out, Summary | Clock in/out, manual marking, monthly attendance reports |
| Leave Management | Apply, Approve, Balance | Leave types (casual/sick/earned), approval workflow, balance tracker |
| Basic Payroll | Salary, Payslip PDF | Salary structure setup, monthly calculation, payslip generation |
| Role & Auth | Admin / HR / Employee | Login, JWT sessions, role-based access control |
| Dashboard | Stats & Snapshot | Headcount stats, today's attendance, pending approvals |

## 2.2  Advanced / Optional Features

Build these only if the core modules are completed ahead of schedule:

| Module | Features | Notes |
| --- | --- | --- |
| Performance Reviews | KPIs, 360 feedback, appraisals | Optional — high complexity |
| Recruitment | Job posts, applicant tracking | Optional — needs extra UI |
| Training & LMS | Courses, completion, certs | Optional — good for v2 |
| Advanced Payroll | TDS / PF / ESI, bonus | Optional — complex logic |
| Document Management | Upload, offer letters | Can be partial in 20 days |
| Notifications | Email/SMS, birthday alerts | Email alerts are feasible in 20 days |
| Reports & Analytics | Attendance, payroll reports | CSV/PDF export — Day 15-16 |
| Asset Management | Device assign & return | Simple CRUD — low effort |

# 3. 20-Day Project Roadmap

Days 1–2 are reserved for onboarding. Days 3–20 are active development. Assign 1–2 tasks per intern per day and maintain parallel frontend/backend tracks.

| Days | Phase | Focus | Tasks |
| --- | --- | --- | --- |
| Day 1–2 | Intro | Onboarding & Setup | Git/GitHub, project setup, tech stack intro, DB schema design, task assignment in Trello/Jira |
| Day 3–4 | Foundation | Auth system + role setup | Login/register APIs, JWT tokens, role model (Admin/HR/Employee), protected routes, UI scaffold |
| Day 5–6 | Core Module 1 | Employee management | Employee CRUD APIs, department & designation tables, employee list & profile pages, search & filter |
| Day 7–8 | Core Module 2 | Attendance tracking | Clock in/out API, attendance model, monthly summary view, admin manual marking |
| Day 9–10 | Core Module 3 | Leave management | Leave types setup, apply/approve/reject flow, leave balance logic, leave calendar view |
| Day 11–12 | Core Module 4 | Basic payroll | Salary structure model, monthly calculation, payslip PDF generation, payroll list view |
| Day 13–14 | Core Module 5 | Dashboard + notifications | Admin dashboard (headcount, attendance, pending leaves), role-based views, email alerts |
| Day 15–16 | Optional | Reports + document uploads | Attendance & payroll report exports (CSV/PDF), employee document upload, basic asset module |
| Day 17–18 | Polish & Testing | Bug fixes + UI polish | Frontend clean up, validation & error handling, API testing (Postman), unit tests on key modules |
| Day 19–20 | Delivery | Demo & deployment | Deploy to staging (Hostinger / VPS), seed demo data, final walkthrough, README & documentation |

# 4. Intro Days — Day 1 & Day 2

Cover these topics across the first two days. Use 30–45 minute slots, mixing short talks with hands-on exercises. By end of Day 2, every intern should have a working dev environment and their first assigned task.

## 4.1  Day 1 — Tools, Workflow & Collaboration

| Topic | What to cover | Hands-on exercise |
| --- | --- | --- |
| Git & GitHub | init, clone, add, commit, push, pull. Branching strategy: main / dev / feature-*. Pull requests & code review | Each intern creates a branch, makes a commit, opens a PR |
| Project Management | Set up Trello or Jira board, create tickets, assign tasks, daily standup format | Create their first ticket and move it to In Progress |
| Dev Environment | VS Code + extensions (ESLint, Prettier, GitLens), Node.js/Python env, .env files, package manager | Set up project locally and run it |
| Team Communication | Slack/Discord channels, how to ask good technical questions, async update norms, code of conduct | Post a standup message in the team channel |

## 4.2  Day 2 — Tech Stack, Architecture & HRMS Overview

| Topic | What to cover | Hands-on exercise |
| --- | --- | --- |
| System Design Overview | Walk through HRMS architecture: frontend, backend API, database. Show folder structure and codebase skeleton | Explore the repo and identify where each module lives |
| Database Design | Relational DB concepts (tables, FK, joins). Walk through HRMS schema: employees, departments, attendance, leaves. Use dbdiagram.io | Draw the schema on dbdiagram.io together |
| REST API Concepts | HTTP methods, status codes, JSON structure, Postman demo. Show one sample CRUD API end-to-end | Hit the sample API in Postman and inspect the response |
| Feature Walkthrough | Demo a reference HRMS or Figma wireframes. Walk through each module so interns understand what they are building | Note down questions about their assigned module |
| Coding Standards | Naming conventions, folder structure, conventional commit format, PR review checklist | Review a sample PR together and leave comments |
| Task Kick-off | Assign Day 3–4 tasks. Each intern picks their first module. Set up shared repo, base branch, and first empty PR | Push an empty branch and open their first draft PR |